Name of the project:	LinkiNjob: job-hunting with the help of librarians

PROJECT TIMETABLE / Gantt chart (Jan. 2015)

| MONTHS | M1 9 | M2 10 | M3 11 | M4 12 | M5 1 | M6 2 | M7 3 | M8 4 | M9 5 | M10 6 | M11 7 | M12 8 | M13 9 | M14 10 | M15 11 | M16 12 | M17 1 | M18 2 | M19 3 | M20 4 | M21 5 | M22 6 | M23 7 | M24 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project activity* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A1 Implementing management structure of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M1 (Brasov) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A2 Financial and technical reporting to the coordinator (interim (M12) and final (M24)) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A2 Internal Reporting (Dissemination table, Time sheets) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A3 Monitoring and evaluation of project indicators (outputs and results) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01/A1 (Research) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A4 Use of web tools and social media for exchange of best practices (virtual cooperation) – web page |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A5 Preparation of curiculum for library staff training in Linz |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C1 (5-days library staff training course in Linz) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M2 (Linz, Saturday) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A6 e-learning in virtual classroom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A7 Preparing and runing learning activities for unemployed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01/A2 (Preparing descriptions of best practices for e-Guidelines in all partners' libraries) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M3(Vantaa) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01/A3 (Designing, editing and translating e-Guidelines) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M4 (Ljubljana) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E1-B1 (valorisation meetings) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A8 Dissemiantion activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |